## DAY 1
OVERALL EVENT FLOW, FRIDAY 2026-09-04, doors 10:00 to 18:00
PHASE | ACTIVITY | OWNS IT | MATCH | STARTS | ENDS | MINS
STREAM STARTS | STARTING SOON, sponsor bed and ad reel | GFX |  | 10:00 | 10:10 | 10
| NATIONAL ANTHEMS, all five nations | Floor / audio |  |  |  | 10
| THE RIVALRY SERIES STORY, video package | VT |  |  |  | 5
| HOST, first words of the day, then what happens today | Host |  |  |  | 4
| TO CASTERS, format explainer, the aggregate rule, both tables | Casters |  |  |  | 5
| BACK TO HOST, player announcements and walk ons, VFX | Host / GFX |  |  |  | 8
| Coin flip sequence (But for first match, there will be an explainer as to why there is no coin flip and NIgeria's home advantage) | Host/GFX |  |  |  | 3
MATCHES ONGOING | TEAM & PLAYER INTRO SEQUENCE, NGA1 and GHA1, NGA2 and GHA2 | GFX / VT | NGA1 v GHA1 |  |  | 2
GAME1 | CASTER H2H and PLAYER CARDS, Nigeria v Ghana, seat 1 | Casters / GFX | NGA1 v GHA1 |  |  | 5
MATCH 1 | MATCH LIVE, score bug, pop ups | Casters | NGA1 v GHA1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, | GFX / VT | NGA2 v GHA2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Nigeria v Ghana, seat 2 | Casters / GFX | NGA2 v GHA2 |  |  | 3
MATCH 2 | MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | NGA2 v GHA2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Nigeria v Ghana |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Host |  |  |  | 3
| INTERVIEW, saucy opinions. | Caster |  |  |  | 3
| REACTION ON THE FLOOR | Hosts |  |  |  | 1
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAYER INTRO SEQUENCE, KEN1 and SEN1 | GFX / VT Host | KEN1 v SEN1 |  |  | 8
GAME 2 | CASTER H2H and PLAYER CARDS, Kenya v Senegal, seat 1 | Casters / GFX | KEN1 v SEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | KEN1 v SEN1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, KEN2 and SEN2 | GFX / VT | KEN2 v SEN2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Kenya v Senegal, seat 2 | Casters / GFX | KEN2 v SEN2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | KEN2 v SEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Kenya v Senegal |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters |  |  |  | 3
| TOMIDE INTRODUCED FOR SPEECH | Host / crowd |  |  |  | 5
| REACTION ON THE FLOOR | Host |  |  |  | 1
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAYER INTRO SEQUENCE, CIV1 | GFX / VT | GHA1 v CIV1 |  |  | 5
GAME 3 | CASTER H2H and PLAYER CARDS, Ghana v Ivory Coast, seat 1 | Casters / GFX | GHA1 v CIV1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | GHA1 v CIV1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, CIV2 | GFX / VT | GHA2 v CIV2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Ghana v Ivory Coast, seat 2 | Casters / GFX | GHA2 v CIV2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | GHA2 v CIV2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Ghana v Ivory Coast |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters / GFX |  |  |  | 5
| CELEBRITY MATCH BUILD, Kombo v Coach B.I, introduce and let them talk | Host |  |  |  | 5
| CELEBRITY MATCH LIVE, 3 minute halves, 99 RATED | Casters | Kombo v Coach B.I |  |  | 10
| REACTION ON THE FLOOR | Host |  |  |  | 1
MATCHES ONGOING | PLAY AREA, warmups, player interviews, squad talk | Play area |  |  |  | 3
GAME 4 | CASTER H2H and PLAYER CARDS, Nigeria v Kenya, seat 1 | Casters / GFX | NGA1 v KEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | NGA1 v KEN1 |  |  | 25
| RESULT CARD | GFX/Casters |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| AGGREGATE SO FAR, then H2H, Nigeria v Kenya, seat 2 | Casters / GFX | NGA2 v KEN2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | NGA2 v KEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Nigeria v Kenya |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters |  |  |  | 3
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAY AREA, warmups, player interviews, squad talk | Play area/Host |  |  |  | 4
GAME 5 | CASTER H2H and PLAYER CARDS, Ivory Coast v Senegal, seat 1 | Casters / GFX | CIV1 v SEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | CIV1 v SEN1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| AGGREGATE SO FAR, then H2H, Ivory Coast v Senegal, seat 2 | Casters / GFX | CIV2 v SEN2 |  |  | 5
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | CIV2 v SEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Ivory Coast v Senegal |  |  | 5
BREAK | CASTER INTERVIEW PLAYERS |  |  |  |  | 3
DAY CLOSE | DAY WRAP, both tables, analyst desk verdict | Analyst desk |  |  |  | 5
| PLAYER OF THE DAY, presented | Casters / GFX |  |  |  | 3
| TOMORROW ON THE RIVALRY SERIES | Host / VT |  |  |  | 4
STREAM ENDS | END CREDITS AND CAMERA | GFX |  |  |  | 3
| ENDING SOON | GFX |  |  |  | 5

## DAY 2
OVERALL EVENT FLOW, SATURDAY 2026-09-05, doors 10:00 to 18:00
PHASE | ACTIVITY | OWNS IT | MATCH | STARTS | ENDS | MINS
STREAM STARTS | STARTING SOON, sponsor bed and ad reel | GFX |  | 10:00 | 10:10 | 10
| NATIONAL ANTHEMS, all five nations | Floor / audio |  |  |  | 10
| THE RIVALRY SERIES STORY, video package | VT |  |  |  | 5
| HOST, first words of the day, then what happens today | Host |  |  |  | 4
| TO CASTERS, format explainer, the aggregate rule, both tables | Casters |  |  |  | 5
| BACK TO HOST, player announcements and walk ons, VFX | Host / GFX |  |  |  | 8
| Coin flip sequence (But for first match, there will be an explainer as to why there is no coin flip and NIgeria's home advantage) | Host/GFX |  |  |  | 3
MATCHES ONGOING | TEAM & PLAYER INTRO SEQUENCE, GHA1 and KEN1, GHA2 and KEN2 | GFX / VT | GHA1 v KEN1 |  |  | 2
GAME1 | CASTER H2H and PLAYER CARDS, Ghana v Kenya, seat 1 | Casters / GFX | GHA1 v KEN1 |  |  | 5
MATCH 1 | MATCH LIVE, score bug, pop ups | Casters | GHA1 v KEN1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, | GFX / VT | GHA2 v KEN2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Ghana v Kenya, seat 2 | Casters / GFX | GHA2 v KEN2 |  |  | 3
MATCH 2 | MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | GHA2 v KEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Ghana v Kenya |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Host |  |  |  | 3
| INTERVIEW, saucy opinions. | Caster |  |  |  | 3
| REACTION ON THE FLOOR | Hosts |  |  |  | 1
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAYER INTRO SEQUENCE, NGA1 and CIV1 | GFX / VT Host | NGA1 v CIV1 |  |  | 8
GAME 2 | CASTER H2H and PLAYER CARDS, Nigeria v Ivory Coast, seat 1 | Casters / GFX | NGA1 v CIV1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | NGA1 v CIV1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, NGA2 and CIV2 | GFX / VT | NGA2 v CIV2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Nigeria v Ivory Coast, seat 2 | Casters / GFX | NGA2 v CIV2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | NGA2 v CIV2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Nigeria v Ivory Coast |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters |  |  |  | 3
| REACTION ON THE FLOOR | Host |  |  |  | 1
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAYER INTRO SEQUENCE, SEN1 | GFX / VT | GHA1 v SEN1 |  |  | 5
GAME 3 | CASTER H2H and PLAYER CARDS, Ghana v Senegal, seat 1 | Casters / GFX | GHA1 v SEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | GHA1 v SEN1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| PLAYER INTRO SEQUENCE, SEN2 | GFX / VT | GHA2 v SEN2 |  |  | 2
| AGGREGATE SO FAR, then H2H, Ghana v Senegal, seat 2 | Casters / GFX | GHA2 v SEN2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | GHA2 v SEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Ghana v Senegal |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters / GFX |  |  |  | 5
| CELEBRITY MATCH BUILD, Don Jazzy vs Zlatan, introduce and let them talk | Host |  |  |  | 5
| CELEBRITY MATCH LIVE, 3 minute halves, 99 RATED | Casters | Don Jazzy vs Zlatan |  |  | 10
| REACTION ON THE FLOOR | Host |  |  |  | 1
MATCHES ONGOING | PLAY AREA, warmups, player interviews, squad talk | Play area |  |  |  | 3
GAME 4 | CASTER H2H and PLAYER CARDS, Ivory Coast v Kenya, seat 1 | Casters / GFX | CIV1 v KEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | CIV1 v KEN1 |  |  | 25
| RESULT CARD | GFX/Casters |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| AGGREGATE SO FAR, then H2H, Ivory Coast v Kenya, seat 2 | Casters / GFX | CIV2 v KEN2 |  |  | 3
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | CIV2 v KEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Ivory Coast v Kenya |  |  | 5
BREAK | CASTER INTERVIEW PLAYER FROM WINNING TEAM | Casters |  |  |  | 3
| AD BREAK |  |  |  |  | 10
MATCHES ONGOING | PLAY AREA, warmups, player interviews, squad talk | Play area/Host |  |  |  | 4
GAME 5 | CASTER H2H and PLAYER CARDS, Nigeria v Senegal, seat 1 | Casters / GFX | NGA1 v SEN1 |  |  | 5
| MATCH LIVE, score bug, pop ups | Casters | NGA1 v SEN1 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| ANALYST DESK, first leg read, sets up seat 2 | Analyst desk |  |  |  | 5
| AGGREGATE SO FAR, then H2H, Nigeria v Senegal, seat 2 | Casters / GFX | NGA2 v SEN2 |  |  | 5
| MATCH LIVE, score bug, pop ups, RUNNING AGGREGATE from first whistle | Casters | NGA2 v SEN2 |  |  | 25
| RESULT CARD | GFX |  |  |  | 3
| FIXTURE AGGREGATE END CARD, then ANALYST DESK, both tables | GFX / Analyst desk | Nigeria v Senegal |  |  | 5
BREAK | CASTER INTERVIEW PLAYERS |  |  |  |  | 3
DAY CLOSE | DAY WRAP, both tables, analyst desk verdict | Analyst desk |  |  |  | 5
| PLAYER OF THE DAY, presented | Casters / GFX |  |  |  | 3
| BACK TO CASTERS, final nations table and individual table | Casters / GFX |  |  |  | 5
AWARDS | Back to host | Host / floor |  |  |  | 1
| Brings on KON10DR to present to 5th place & picture taken | Host / floor |  |  |  | 2
| Brings on BAYSE to present to 4th place & picture taken | Host / floor |  |  |  | 2
| Brings on Paga to present to 3rd place & picture taken | Host / floor |  |  |  | 2
| Brings on Game Evo to present to 2nd place & picture taken | Host / floor |  |  |  | 2
| Announces winning team/plus fire, interviews them and they give speech | Host / floor |  |  |  | 4
| Brings on Cade Esports to present to 1st place/confetti & Fire & picture taken | Host / floor |  |  |  | 3
| Winning team picture | Host / floor |  |  |  | 2
| All players picture together | Host / floor |  |  |  | 2
| All players plus coaches/managers pictures together | Host / floor |  |  |  | 2
| Family and fans | Host / floor |  |  |  | 2
| HOSTS closes the day with speech | Host / floor |  |  |  | 1
STREAM ENDS | KUNMI: ITS A WRAP/END CREDITS AND CAMERA | GFX |  |  |  | 3
| ENDING SOON | GFX |  |  |  | 5

## STREAM ELEMENTS
PROPOSED STREAM ELEMENTS
P1 it does not work without this ¦ P2 the show is visibly worse without it ¦ P3 worth having if there is time
REF | ELEMENT | PRIORITY | NOTE
A. The five the format forces, and none of them exist
A1 | Running aggregate on the score bug | P1 | From the first whistle of match 2. The bug shows the live match score AND the fixture aggregate together. Without it a viewer sees Ghana winning 2-0 and has no way to know Ghana are losing the fixture
A2 | Fixture end card | P1 | The aggregate result, both legs, the points awarded. Ten of these across the weekend, and each one is the moment a fixture is actually decided
A3 | Two tables, not one leaderboard | P1 | The nations table and the individual table are different objects and both are live. One leaderboard graphic cannot carry it. Both need a goal difference column visible, see the note below
A4 | Seat 1 and seat 2 identity | P2 | Seat 1 only ever plays seat 1. On screen, without it, the match ups look arbitrary. A small persistent SEAT 1 / SEAT 2 marker on the player name plate
A5 | The aggregate explainer | P2 | A 20 to 30 second animated version of the Nigeria 3-2 Ghana example. Runs at the top of every day and after every long break, for anybody who just joined
B. Carried over from the Elite League, and they work
B1 | Starting soon, with sponsor bed and ad reel | P1
B2 | Be right back, ending soon, offline | P1
B3 | Player introductions with VFX walk ins | P1
B4 | Caster head to head before each match | P1
B5 | Player cards, one per competitor | P1
B6 | Score bug during play, plus pop ups | P1
B7 | Result card at the end of each match | P1
B8 | Predictions and polls between matches | P2
B9 | Highlights replay | P2
B10 | Matchday matchups in order, the day at a glance | P2
B11 | End credits | P2
B12 | Transitions and stingers between segments | P2
C. Desk furniture, because we now have two desks
C1 | Lower thirds for every person on camera | P1 | Casters, analysts, host, players, guests. The most reused graphic in the whole package
C2 | NOW / NEXT bar | P2 | What is on and what follows. Standard desk furniture and it keeps a long day legible
C3 | Analyst desk full frame | P2 | A layout that holds three people plus a graphic, which is a different frame to the two hander caster layout
C4 | Break screen with a countdown | P1 | There are two long breaks a day. A clock is the difference between a break and dead air
C5 | Ticker | P3 | Standings, next fixture, sponsor line. Useful on a day with this much non-match time
C6 | Play area frame | P2 | Warmups and player interviews come from a different space, so they need their own identifying frame
C7 | Crowd interview bumper | P3 | In and out of crowd segments. A natural sponsor slot
D. Competition graphics
D1 | Nations table | P1 | Five rows, points, goal difference, goals, fixtures played
D2 | Individual table | P1 | Ten rows, same columns against the player's own matches
D3 | Fixture card before each fixture | P1 | The two nations, the two match ups, seat by seat
D4 | Squad reveal | P2 | One squad, locked at registration, used for all four matches. Good television and it makes the one squad rule visible
D5 | Setup countdown, 5 minutes | P2 | A real rule with a real clock. Free tension, and it makes the rule enforceable on camera
D6 | Head to head history | P3 | Only meaningful once nations have met before, so mostly for later editions
D7 | Goal of the day | P3 | Cut and played at the day wrap. Cheap, and it gives Days 1 and 2 an ending
D8 | Player of the day | P2 | Presented on camera. Days 1 and 2 have no trophy, so this is their climax
E. Bayse, now that the SLA is signed
E1 | Market state on the pre match card | P2 | Part of the caster head to head, before a ball is kicked
E2 | Market movement pop up | P2 | At half time in match 2, when the aggregate is live and the market has actually moved. This is the money shot for Bayse and for us
E3 | Closing card at the fixture end | P2 | Where the market landed against the actual result. Reads as a scoreboard rather than an advert
E4 | Poll and prediction slot | P2 | Already a B8 element. Branding it is the cheapest integration on this list
G. What has to be shot or written, not designed
G1 | The Rivalry Series story video | P1 | Day 1, near the top of the show. Needs footage from previous Nigeria against Ghana editions
G2 | Yesterday in ninety seconds | P1 | Days 2 and 3. Cut overnight, so it needs an editor on site and a turnaround plan
G3 | Five national anthems | P1 | Clean audio, correct versions, checked with each delegation
G4 | Player walk on VFX | P1 | Ten players. Names are the blocker: six legal names are still not held
G5 | Guest introductions | P2 | Seven confirmed guests, one unconfirmed
G6 | Opening sequence | P1 | Dance group or musician. Not booked, and it is the first thing on screen
H. Screen, things that pop up on the screens
h1 | Match Winner VFX
H2 | Champion VFX

## LEGEND
COLOUR CODES
PHASE, the row band
STREAM STARTS / PRE-MATCHES
MATCHES ONGOING
CELEBRITY MATCH
DAY CLOSE
AWARDS
STREAM ENDS
OWNS IT, the third column only
Host
Casters
Analyst desk
Play area
GFX
VT
Floor
STREAM ELEMENTS tab: P1 red bold means it does not work without that element.
RED BOLD TEXT means not confirmed. Scheduled and costed, not booked.
Every tint is pale on purpose: black text stays readable and the sheet still prints on a mono office printer, which is what happens to a run of show on the day.